RPAForce

RPA Implementation Guide

Step-by-step methodology for process automation

UiPath · Automation Anywhere · Power Automate · Blue Prism

Version 2.1 — March 2026

# Introduction

This guide describes the RPAForce standard methodology for implementing Robotic Process Automation (RPA) projects. It applies to all platforms (UiPath, Automation Anywhere, Power Automate, Blue Prism) and all complexity levels.

The goal is to ensure every project is delivered with high quality, on time and with full client acceptance.

# Phase summary

| Phase 1 | Discovery & Assessment Complete mapping of the current process with the AI Assistant and the client team. | ⏱ 1-2 weeks |
| --- | --- | --- |

| Phase 2 | PDD — Process Design Document Detailed technical specification of the robot: flow, exceptions, systems, credentials. | ⏱ 1-3 weeks |
| --- | --- | --- |

| Phase 3 | Development Building the robot on the selected platform. | ⏱ 2-8 weeks |
| --- | --- | --- |

| Phase 4 | UAT — User Acceptance Testing Testing with the client using real data. Issue resolution. | ⏱ 1-2 weeks |
| --- | --- | --- |

| Phase 5 | Deploy & Go-Live Production configuration, go-live checklist and supervised first run. | ⏱ 1 week |
| --- | --- | --- |

| Phase 6 | Support & Maintenance Monitoring, updates for system changes and incident management. | ⏱ Ongoing |
| --- | --- | --- |

# Phase 1 — Discovery & Assessment

## Objective

Obtain a complete and accurate description of the process to automate: steps, systems, volume, exceptions and technical factors.

## Required participants

- Process Owner: approves scope and has decision-making authority

- Key Users: run the process daily and know all special cases

- RPAForce Advisor: facilitates the session and ensures information is complete

## Method

RPAForce's AI Assistant conducts the Discovery session with structured questions. The result is a JSON with all process data that automatically feeds the AS-IS report and proposal.

## Deliverables

- Discovery report with BPMN process diagram

- Complexity analysis and estimated automation %

- Preliminary ROI calculation

- Technical risk identification (Citrix, terminals, anti-bots)

# Phase 2 — PDD (Process Design Document)

## Objective

Document in detail how the robot will work: every step, every decision, every exception.

## PDD contents

- Functional description of the robot

- TO-BE flow diagram (how the automated process will work)

- Complete list of required systems and credentials

- Exception cases and how the robot handles them

- Implemented business rules

- Acceptance criteria (what constitutes a successful run)

- Expected input and output data

## Approval criterion

The PDD must be signed by the Process Owner before development begins. Without an approved signature, coding does not start.

# Phase 3 — Development

## Coding standards

- Variable naming: camelCase, in English, descriptive

- Error handling: try-catch on every critical activity

- Logs: record start, end, processed transactions and errors

- Credentials: only from Orchestrator Assets or vault — never hardcoded

- Modularization: separate independent sub-processes

## Version control

All code lives in the version control repository. Each commit must include the issue or task number and a short description of the change.

## Code review

Before moving to UAT, code must be reviewed by a second developer. The review checklist includes: error handling, credentials, logs, performance and PDD compliance.

# Phase 4 — UAT (User Acceptance Testing)

## Objective

Validate with the client that the robot works correctly using real data and conditions.

## UAT protocol

- Prepare a test data set covering: happy path, exception cases, edge cases

- Run the robot in the testing environment with the prepared data

- The Key User verifies results transaction by transaction

- Log all issues in the UAT spreadsheet

- Classify issues: Blocking / Major / Minor / Enhancement

- Fix all Blocking and Major issues before go-live

- Client signs the UAT acceptance certificate

⚠️ Go-live criterion

Do not go live with open Blocking or Major issues.

Minor issues can remain as backlog for the first maintenance update.

# Phase 5 — Deploy & Go-Live

## Prerequisites

Complete the Go-Live Checklist before running in production. See document: RPAForce_GoLive_Checklist.docx

## Go-live process

- Deploy the robot in the production environment

- Verify access and credentials in production

- First run supervised live by both RPAForce and client teams

- Validate first run results

- Enable automated scheduling

- Deliver technical documentation and operational manual to client

- Sign the go-live acceptance certificate

# Phase 6 — Support & Maintenance

## Standard coverage

- Execution monitoring and failure alerts

- Post-production bug fixes

- Robot updates when involved systems change

- Monthly execution reports (processed transactions, time, errors)

## Change Requests

Scope changes outside the original contract are formalized through a Change Request (CR). The CR includes: change description, robot impact, hour estimate and price. Requires client approval before execution.

# Supported platforms

| Platform | Best for |
| --- | --- |
| UiPath | Enterprise projects with Orchestrator, high complexity |
| Automation Anywhere | Environments with Citrix or legacy applications |
| Power Automate | Integration with Microsoft 365 ecosystem |
| Blue Prism | Projects with strict audit and compliance requirements |
| Custom RPA (Python/Playwright) | Simple web processes or low volume |

# Special technical factors

| Factor | Implementation impact |
| --- | --- |
| Citrix / VDI | Requires Computer Vision — increases complexity and development time |
| Terminal / AS/400 | Requires integrated terminal emulator |
| CAPTCHA | Specific solution per type — may require human intervention |
| Physical token / MFA | Requires IT coordination for special service account |
| Available API | Reduces complexity — prefer API over UI when possible |
| Unstable / slow system | Requires special timeout and retry handling |